## Second Sprint
Second Sprint BackLog |  |  | Not Started
Team: NoName |  |  | In Progress
Completed
Sprint 2 : Task Description | Duration (hours) | Who | Status | 2011-10-24 | 2011-10-25 | 2011-10-26 | 2011-10-27 | 2011-10-28 | 2011-10-31 | 2011-11-01 | 2011-11-02 | 2011-11-03 | 2011-11-04 | 2011-11-07 | 2011-11-08 | 2011-11-09 | 2011-11-10 | 2011-11-11 | 2011-11-14 | 2011-11-15 | 2011-11-16 | 2011-11-17
1. Summary of the best and worst performing shares
1.1 Calculate the amount the stock is worth after a week | 5 | Martin | Completed | 4 | 4 | 3 | 3 | 3 | 3 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 Track the difference and desplay the results to the user | 5 | Martin | Completed | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.Have more info if data is unavailable
2.2 Track stock price change | 3 | Stewart, Martin | Completed | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
3. Alerted if any shares plummet or rocket
3.1 Track stock price change over the course of the day | 5 | Borislav, Lyuben | Completed | 5 | 4 | 5 | 5 | 3 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 Alert if a share price plumments | 5 | Borislav | Completed | 5 | 4 | 5 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 4 | 3 | 3 | 1 | 1 | 0 | 0 | 0
3.3 Alert if a share price rockets | 5 | Lyuben | Completed | 5 | 5 | 4 | 4 | 4 | 4 | 5 | 3 | 3 | 3 | 3 | 4 | 3 | 3 | 1 | 1 | 0 | 0 | 0
3.4 Display if a share value remians constant | 5 | Stewart | Completed | 5 | 5 | 4 | 4 | 4 | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 1 | 1 | 0 | 0 | 0
4. Redesign User Interface
4.1 Create Prototypes | 5 | Lyuben,Stewart | Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 4 | 4 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0
5. Tests
5.1 Write acceptance tests for new user stories | 3 | Borislav | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
5.2 Write Unit Tests | 3 | Lyuben, Stewart | Completed | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
5.3 BlackBox Testing | 3 | Borislav | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
5.4 Refactor code | 3 | Borislav, Lyuben | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0
6. Sprint Review Presentation
6.1 Prepare Paperwork | 2 | Borislav | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
6.2 Test equipment | 3 | Stewart | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
6.3 Prepare prototypes | 2 | Lyuben | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Total | 57 |  |  | 47 | 45 | 43 | 41 | 39 | 39 | 39 | 34 | 31 | 27 | 26 | 23 | 21 | 20 | 12 | 11 | 5 | 2 | 0