## Sheet1
Sprint BackLog
Not Started
In Progress
Completed
Sprint 1 : Task Description | Duration (hours) | Who | Status | 2011-10-03 | 2011-10-04 | 2011-10-05 | 2011-10-06 | 2010-10-07 | 2011-10-10 | 2011-10-11 | 2011-10-12 | 2011-10-13 | 2011-10-14
1. Research
1.1 Android Platform | 1 | Stewart | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 Search for API | 1 | Lyuben | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 Install Software | 1 | Lyuben | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Extract inforamtion from API
2.1 Connect API to Application | 2 | Stewart | In Progress | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2.2 Track stock price change | 3 | Stewart | In Progress | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
2.3 Retrieve information from API | 2 | Borislav | Not Started | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
2.4 Calculate the SUM | 1 | Martin | Not Started | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2.5 Track prices and alert | 2 | Martin | Not Started | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
2.6 Graphical user interface | 3 | Borislav | Not Started | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
TEST the platform | 2 | No name | Not Started | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Total | 18 |  |  | 16 | 15 | 14 | 13 | 13 | 13 | 13 | 13 | 13 | 13